## Slide 1: Project Management
For ESM 401
20 January 2005

## Slide 2: Overview
Overview of Project Management
Construction contracts
Cost terms
Owner’s viewpoint
Public and Government’s viewpoint

## Slide 3: What is a project?
One-of-kind undertaking
Definite objective
Start and end points

## Slide 4: Characteristics
Temporary
Use scarce resources
Specific objectives
Unique outcomes
Special budget
One person has responsibility

## Slide 5: Project Life Cycle

## Slide 6: Organizations
Table of Organization
Regiment
Battalion
Battalion
Battalion
Co.A
Co.C
Co.B
Co.A
Co.C
Co.B
Pl.1
Pl.2
Pl.3
Pl.1
Pl.2
Pl.3

## Slide 7
Functional Organization
  Group by discipline or function
  Line vs. Staff
Colonel
Construction
Design
Permits
Staff B
Staff A

## Slide 8: Functional
http://www.miamidade.gov/wasd/about_table_org.asp

## Slide 9: Staff Functions
(Corps of Engineers, Alaska)
Alaska District Corps of Engineers - Organization Chart

## Slide 10: Organizations
Product
CEO Boeing
747 Jets
757 Jets
Small Planes

## Slide 11: Matrix Organization
CEO
Chief Mechanical
Chief Civil and Soils
Chief Electrical
Project 1 Sid
Project 2 Kid
Project 3 Sue
2 ME
2 CE
5 EE
5 ME
0 CE
2 EE
5 ME
5 CE
5 EE

## Slide 12: Projectized Organization
Just matrix with decreased or absent functional heads

## Slide 13: Concepts
Flattened organization
  Antithesis of triangular organization
Self-directed team
  limiting case of flattened organization

## Slide 14: Three aspects of P.M
Schedule
  time
Cost
  budget
Production
  performance, specification

## Slide 15: Bar Chart Schedules
Most common
Simple
(Excel)
Gantt chart

## Slide 16: CPM
Critical Path Method
PERT (Program Evaluation and Review Technique)
  uses statistical methods

## Slide 17: CPM as Management Tool
Delays on critical path delay job
Document delays
Delay on activities with float will not delay job, up to the amount of float
Experiment with different allocations of overtime, “crashing” activities

## Slide 18: Managerial Accounting, WBS
Work Breakdown Structure

## Slide 19: Cost control
Financial accounting
  accurate to penny
  slow, up to three months after the fact
Managerial accounting, cost accounting
  fast, ASAP
  Why?

## Slide 20: Use of Cost Control
Must be timely
Must indicate strong and weak points
Therefore must tie costs to specific activities
(Excel)

## Slide 21: WBS
Cost codes

## Slide 22: Engineering and Construction Contracts

## Slide 23: Engineering Contracts
A/E = Architect/Engineer
Owner
Contractor
A/E

## Slide 24: A/E contract
Sophisticated vs. non-sophisticated
  Many are non-sophisticated
Often lack clear definition at start

## Slide 25: Design Phases
Preliminary
  Planning
  Programming
Design
  10, 35, 75, 95%
  Bid documents
Construction

## Slide 26: Construction Contracts
Traditional
Owner
Contractor
A/E

## Slide 28
Design-build
Owner
Contractor
A/E
A/E
OR

## Slide 30
Construction (Project) Management
Owner
Contractor
A/E
C M

## Slide 33
Turnkey
Fast track
End result

## Slide 34: Construction Contract Payment
Fixed price
Unit price
Cost plus

## Slide 35: 200,000 CY of ?
Fixed price
Fixed price
Unit price
Cost plus
rock
rock
Cut line
Borehole
1 mile

## Slide 37: Public Construction Contracts
History
Federal
  CFRs
  41CFR
  FARs
State
  Title 36
Local

## Slide 38: The Public Contracting Process
Advertise
Receive Proposals
Open Proposals (Bids)
Evaluate and Award
Work
Changes
Completion
Warrantee

## Slide 39: Private Contracting
Not controlled by law, except
  subcontracts or suppliers on public works
Corporate rules
  SEC
  Accounting and Auditing
Biggest difference is that private can select bidders

## Slide 40: Mechanics Liens and Bonding
Common law situation:
Bank lends money to project
  Secured creditor
A/Es, laborers, material suppliers
  Not secured
Builder goes belly up
  Bank gets value in building
  Others get nothing

## Slide 41: Mechanics Liens and Bonding
Mechanics lien laws give laborers and others the right to get paid.
Lenders and owners often require “payment bonds” of contractors.
Different than:
  Bid bonds
  Performance bonds.
Most public construction requires all three.

## Slide 42: “Construction Documents”
Agreement
Drawings
General Conditions
Special Conditions
Technical Specifications
  Reference specifications and technical documents
Hierarchy statement

## Slide 43: Bid Documents
Many formalities for public construction
“Front end” plus Construction Documents
Bid form
Bid bond
Many miscellaneous forms, see ADOT
“Non-responsive” vs. “Informalities”

## Slide 44: ADOT
DOT&PF - Statewide Design & Engineering Services - D&CS - Preconstruction

## Slide 45: Clauses and Problems
Indemnity
  more later during negligence
Liquidated Damages
No Damages for Delay
Punch Lists
Substantial Completion
Beneficial Occupancy
Termination

## Slide 46
Background Material
Government Estimate
Funding Document
Request for Proposal
Proposal Cost or Pricing Data
Proposal Analysis
Prenegotiation Objectives
Price negotiation Memorandum
Modification (to contract)
Notice to Proceed
Corps of Engineers, Modification Package

## Slide 47: Changes
Change Order process
  Corps example
Differing site conditions
  Category I vs. II
Claims Administration
  Administrative procedures.

## Slide 48: Owner’s Viewpoint on Project

## Slide 49: Need, Planning, and Programming
Need
  Project Selection
Project Concept
Planning and Programming
  Size? Timing? Cost?

## Slide 51: Plan for the Plan
As early as possible in the project
Sufficient time and budget must be available to properly plan the project
Often must ask for these resources before very much is definitely known
Consequently, little planning is done
Until the need for the project is great.

## Slide 52
Often the first real planning and programming revels that the project is behind schedule already.
Old Superintendent to young engineer Perkins, about 1970 or so, “We weren’t supposed to be this far behind schedule for months yet.”

## Slide 53: Consequently
First step for a new project is to secure adequate resources for proper planning of the project.
The “project selection process” always requires estimates of funds required for the project.
So we are asking for resources for a project, before it is “selected.”
  Greatest resource need is often people.

## Slide 54: Public vs. Private
Public projects
  Distinction between new construction (“capital project”) and “maintenance” is established by law.
  Capital projects always require approval of a legislative (law making) body
Private projects
  Often requires approval of a board of directors
    large projects always do

## Slide 55: A fourth aspect of project management
Cost
Schedule
Performance
How will project fit into the organization and its strategies.
Notes: <number>
<footer>
<header>
<date/time>
In order to determine this, we must know the organizations strategy. Where is it going and how will it get there.

## Slide 56: Programs
A “program” may have several projects
Program: Improve the Alaska Highway to national highway system standards
Project: Resurface roadway, Mile 480 to Mile 512
Project: Open new gravel source, East of Delta Junction
Project: Reroute Mile 430 to 455

## Slide 57: Within Projects
No standard nomenclature
Tasks
Sub-tasks
Work Orders
Other logical breakdowns
  WBS

## Slide 58: Projects and Taxes
“Expense” vs. “Capital Expenditure”
Profit is the “net” or difference between income and costs.
Pay taxes only on profit
Small goods with a life less than one year, consumable supplies, and salaries are examples of costs that are expenses.

## Slide 59: Capital Expenditures
Goods that have lives longer than one year are capital expenditures.
A new building, automobile, computer for example.
The initial cost may not be taken as an expense in the first year, rather the initial cost must be depreciated over the life of the good.
  Projects are almost always capital expenditures

## Slide 60: Public

## Slide 61: US Government Terms
Three Branches
Executive
Legislative
Judicial

## Slide 62: Executive
President
Cabinet Departments
  Defense
  Commerce
  Health Education Welfare
Independent
Environmental Protection Agency (EPA)

## Slide 63: Legislative
Congress
Two houses
  House of Representatives
  Senate

## Slide 64: State Governments
Governor
Legislature
Courts

## Slide 65: Municipal
Always legislative, but never called that
  Council
  Assembly
  Etc.
Executive is often elected
Sometimes appointed by the legislative
Some municipalities have petty courts

## Slide 66: Other Government Orgs.
May be independent corporation within state or local
  School district
    Elected
    Funding from local government
    Routine funding within budget from local government
    Capital projects must have special funding
  University
    Board of Regents
    Funding from legislature, tuition, other
    Special funding for capital projects
  Port Authority
    Funding from enterprise

## Slide 67: Financing a Project
Taxes and the General Fund
  Current money from taxes
General Obligation Bonds
  Pay back by the taxpayers over time
Revenue Bonds
  Pay back from revenue from the project
  New airport or dock
All require legislative approval

## Slide 68: Projects and Politics
Legislative districts
  Representatives and Senators want money spent in their home district
Executive want job done, does not care which district
Source of Conflict
Fiscal Year
  Money must be spent (or committed) in a particular year.
  “Authorized but not funded”
    Cannot bind future legislatures

## Slide 69: DD 1391
The basic programming document in the military construction process, the DD 1391.
This one page documents goes to congress and is part of the military appropriations law for that year.

## Slide 70
It is a brief summary of the project, but has the essentials of cost, schedule and performance.
But note the lack of detail
This document will become the “law” under which the project is built.

## Slide 71: Permits

## Slide 73: Permits
Construction in the U.S. is highly regulated
Larger projects often require permits from Federal, State, and Local Agencies.
These permits are specified in the regulations and usually require certain details be provided before work is allowed to proceed.

## Slide 74
They often have stipulations that require work be done in a certain manner, or at a certain time.
Permits often require a fee.
Permits often require a public notice and comment period.

## Slide 75
Both the permitting agency and those who are likely to comment are important stakeholders in the project.

## Slide 76
Some permits are “routine”
Some are not routine
Many delays and problems in major projects are due to “permitting.”

## Slide 77
The Fort Knox Gold Mine required over 300 separate permits.
Need to enumerate the permits early in the project
Often in the concept stage

## Slide 78: Most important
Who in the project is responsible for getting which permit
  Owner
  Designer
  Contractor
Often it is the Owner, but with the Designer’s support.

## Slide 79: Examples
But first: (It is better for your morale if you consider the important purpose that is driving the regulation and permitting process rather than regarding the regulators as “obstructionists that do not want the project built.”)
In the U.S. bribery is uncommon in the permitting process.
Politics is common, but (Perkins opinion) its effects are exaggerated by people who “have not done their homework.”

## Slide 80: Local Government
Planning and zoning
Building Permit
  Often for each trade: general, plumbing, electrical
  Fire protection may be separate
Block roads
Transport heavy, very large or dangerous materials over local roads (State permit will also be required)
Utilities
  Temporary and Permanent

## Slide 81: State Environmental
Wastewater and water (out-of-town projects)
Air quality for boilers and generators (both temporary and permanent)
Waste disposal plan
Oil pollution control
Stormwater control
http://www.state.ak.us/local/akpages/ENV.CONSERV/permits.htm
http://info.dec.state.ak.us/sps/document.asp

## Slide 82: State Lands Department
Permit to cross state lands
Temporary roads
Permanent, need “right of way”
Cut timber or clear land
Burn wood
Materials mining (gravel)

## Slide 83: State Fish and Game
General permit
Permit to cross streams
Permit for permanent culverts and bridges

## Slide 84: State Labor
Blasting
Elevators

## Slide 85: State Health
Radiation

## Slide 86: State Transportation
Large or Heavy Loads
(Breakup restrictions)

## Slide 87: Federal Lands
Access, Right of Way, etc. on Federal Lands
Minerals, including gravel and soil, for construction

## Slide 88: Federal Environmental
Some are same as state
Dredge spoil

## Slide 89: Environmental Assessments
NEPA, National Environmental Policy Act
NEPA's basic policy is to assure that all branches of government give proper consideration to the environment prior to undertaking any major federal action that significantly affects the environment
Must screen all actions

## Slide 90: Screening Process
Is the action excluded by the law?
  a few are
Next determine the significance to the environment
  “little handle” concept

## Slide 92: Corps of Engineers
Any change to “navigable” river
  dock, bridge
Dredging
Work in “wetlands”

## Slide 93: Federal Aviation
Structures over a certain height
Near airports

## Slide 94: Federal Communications
Temporary radio

## Slide 95: Take home message
All these take TIME.
Often resources
  initial designs
  data, number of people in a construction camp
  schedule
    When the fish are migrating?

## Slide 96: Planning
Acquisition of the proper permits must be accounted for in the project plan.
Often a task for each permit should be in the CPM

## Slide 97: Changes
Get permit for 200 man camp.
Later it must be enlarged to a 250 man camp.
Now need to review ALL the permits
  Which ones need to be modified
  If this is a major modification, you may have to go through the entire public review process.

## Slide 98: Is this may “cutting red tape” or cutting the ribbon at the opening of his project?

## Slide 99: Codes and Standards

## Slide 100
Codes
Standards
Specifications

## Slide 101: Codes
Codes are the law.
Written by a professional organization
Adopted by a government
Government will often add modifications to code.
  To suit local conditions

## Slide 102: Design Review
Code will often specify review of design by local official.

## Slide 103
Most code provision call for “at least” something
You are free to do more
Most codes are conservative
  protective of life and safety
But this not always true

## Slide 104
http://www.dps.state.ak.us/Fire/asp/

## Slide 105: Standards
Recommendations by a professional group
Often adopted by government
Or “referenced” in code.
Which makes them the law as well.

## Slide 106: Standards Setting Bodies
ASTM
ASME
ACGIH
NFPA
AASHTO
API

## Slide 107: ASTM/ASME
American Society of Testing and Materials
http://www.astm.org
American Society of Mechanical Engineers
http://www.asme.org
Ethical problems, resolved

## Slide 108
If the standard is relevant, it is a minimum requirement.

## Slide 109: Problems
So many standards, that are changing all the time
Hard to keep up

## Slide 110: Project
Owner might set minimum standards for the project
Cite for designer
“All welding and radiography on the project will meet API standards.”
Or cite international standards
  often use U.S.

## Slide 111: Specifications
Standard Specs
  CSI
  http://www.csinet.org/about.htm
  http://www.csinet.org/technic/master/arcomms.htm
  Corps of Engineers
  http://www.ccb.org/ufgs/ufgs.htm

## Slide 112: Project
Project owner may require a standard specification format, that all designers must use.

## Slide 113: Problems
Conflicts: One contractual document seem to contradict another.
Paradox: The more definite you are, the more voluminous the specifications, the greater the chance of a conflict.
Plans with specifications
Specifications with each other
Specifications with its referenced standards

## Slide 114: Conflicts
Conflicts may result in changes
Public construction, contractor must bid in the least burdensome interpretation.
Will always want more money if there is a change.

## Slide 115: Resolution
Precedence clause of contract may help
Most contracts have such a clause.

## Slide 116: Project Specifications
Large projects will often adopt standard specifications for the project.
Project Style Guide
  English, report forms
  aboveground
  above-ground
  above ground

## Slide 117: Take Home Message
Give attention early to codes and standards for the project.
Cite them in contracts
Standard Specifications can improve communications and reduce errors, if used properly

## Slide 118: Project Labor

## Slide 119: U.S. Law
Taft-Hartley
Grants employees the right to “organize”
  form a labor union
Craft unions vs. Industrial unions

## Slide 120: White collar and professional
Many federal, state, and local government workers, including white collar and professional workers, belong to unions.
Rare in private enterprises.

## Slide 121: Construction Unions
Construction unions are craft unions
  Electricians
  Plumbers
  Equipment Operators
  And many others
Each union maintains a “hiring hall.”

## Slide 122
Employers must sign a contract with the craft union in order use the hiring hall.
Contracts are typically for three years.
  Employer cannot hire workers other than those “referred” by the hall.
Makes the union the exclusive agent for the workers.
  It would be breach of contract for employer to negotiate with union employee directly.

## Slide 123
Contract will establish classes of workers and all workers within the class must be paid the same wage.
Contract will specify “work rules”
  limitations on tools and work practices
  limit paint brushes to 4” (10 cm) wide

## Slide 124
Contract will designate certain employees as special representatives of the union
  “Union Steward”
  Must be give preferences, always on the job site
  Time off work to attend to union activities.
    often paid

## Slide 125
Contract will have a “no strike” clause
However
  “slow downs” are not strikes

## Slide 126: Many Crafts
A large project will require labor that belong to 15 or 20 different unions.
Any one of the unions might stop work if their contract expired in the middle of the project
  Could make exorbitant demands.
  Other unions, seeing their contracts will expire during the project, will not work either
  Ignore their “no strike clause” or “slow down.”

## Slide 127
Also, seeing the large project coming, one craft might conspire with its contractors
  Like sub-contractors on the project
  To inflate their wage demands
  All the local union contractors will pay the high rate of pay
  But they all the bid the same work, so their competitive position stays the same.

## Slide 128: Work Non-union
Labor Strife
Workers will “picket” the job site
Other workers will “honor the picket line” and not go to work – solidarity
Some workers will cross the line
Fights and reprisals “picket line violence”
Charges of “unfair labor practices”
  special meaning in labor law

## Slide 129
30 years ago there were many regions of the U.S. where all the major construction work was union.
  Contractor would not attempt to work non-union
  Fear
  Competition, all bidders have the same problems
  Contractors who have good relations with the union are at a competitive advantage.
  Union contractors would support unions against non-union contractors

## Slide 130: Things Change
Today much work is non-union, more often
“Open Shop”
Some subcontractors will be union, some not.
Union and non-union get along – usually
Generally a shortage of skilled labor

## Slide 131: Union Victories
OSHA
  Strongly supported by unions
Davis-Bacon
  Sets minimum wages for certain work for the federal government.
  All construction-type work is covered by Davis-Bacon
  Minimum wage is usually the union wage for the region.
  Follow union guidelines for crafts.
  Most states have similar law

## Slide 132: Union issues
Unions do not admit all qualified
Carefully control the number of workers in their craft
If demand exceed supply, local union will attempt to temporarily import union workers from other areas.
May let local people work, but make clear they are not members and arrangement is only temporary

## Slide 133: cont.
The union contract may permit the employer the right to “call out” certain workers
  Prior employment
  foreman and supervisors.
Some unions do not permit either
All who “work with tools” must be dispatched by the union.

## Slide 134
Corruption is an issue in some regions of U.S.
Labor leaders extort bribes and fees in exchange for “labor peace”
Most regions this is not a problem

## Slide 135: Project Labor Agreement
The owner (usually) negotiates an agreement with all the unions that will be involved in a project, before the project is let out to bid.
In turn for agreeing that the project will be 100% union, the owner will get some concessions.
Wages, overtime pay, transportation allowances, etc.
Owner wants agreement early
Each unions wants to delay agreement, hoping it will get better deal by “holding out.”

## Slide 136: Strikes
Most construction contracts grant excusable delays for “strikes.”
Since the union contract always has a “no strike” clause, strikes are unusual.
Unhappy union will resort to slowdowns
  sickouts
Better, “strikes or other concerted acts of workmen.”

## Slide 137: Strike or Other
Burden is on owner, project will be delayed
Contractor must pay his overhead, but most costs are suspended while the strike is on.
What if only one of the crafts slows down?
  When does it become critical, CPM
  Rogue union will be aware when it can hurt the owner.
  Use the owner to force the contractor to some concessions
  Contractor will then want more money from the owner.

## Slide 138: Major Projects without Unions
A major project will distort local labor supply.
Without PLA, different contractors may compete with each other for labor
  bidding up the wages
  Cannot “conspire” to reduce wages
Owners are reluctant to interfere with contractor’s wage negotiations.

## Slide 139: International Labor
Always wise to use as much local labor as possible
Locals may oppose the project to begin with
Locals resent foreign workers
Most countries restrict importation of labor

## Slide 140: Use of Locals
Locals are often much cheaper on a per manhour basis
Do they have the skills?
Work ethic?
How much training is required?
Language barriers

## Slide 141: Ethnic Issues
Not all “locals” are the same ethnic group
Difficult to tell what may happen
Local partner is often required to navigate through these minefields.

## Slide 142: Project Management
If you are the owner
Do not assume “Labor is the contractor’s problem.”
Anticipate labor supply, costs, and problems in your project planning.
Deal proactively with project labor
  but be careful

## Slide 143: Effects on Project Management
Wages and labor agreements might not be known, when project budget is determined

## Slide 144: Projects and Stakeholders

## Slide 145: Key Concept
“You must accept as fact that you must manage the project from an overall perspective of all the stakeholders – not just the customers and the organization.
“Manage” does not mean you can or should do everything all of the stakeholders desire, but you must consider their desires.

## Slide 146: Who are stakeholders?
Anyone who is interested in project and especially,
Anyone who can harm a project
Organize for explanation, but there is no real organization, it is chaos.

## Slide 147: Primary Stakeholders
Have legal or contractual obligations to the project team.
  Users
  Suppliers, Subcontractors
  Unions
  Shareholders
  Creditors
  Employees
  Government Agencies
Notes: <number>
<footer>
<header>
<date/time>
Examples: project team, shareholders, unions, agiencies, suppliers, customers

## Slide 148: Secondary Stakeholders
Have strong interest in project,
But not legal tie
  Public
  Competitors
  Tourists
  Media
  Families of primary
  Local community
Notes: <number>
<footer>
<header>
<date/time>
Private citizens, consumer groups, environmental groups, “watchdog” groups, anyone who believes they will be affected by the project.

## Slide 149
Relations and communications with stakeholders must be appropriate
Not all are the same
Expectations

## Slide 150: Steps
Identify Stakeholders
Understand their interest
Measure their interest
Predict reaction
Identify effect of reaction on project

## Slide 151: Outline
Meet the Stakeholders so they learn your face
  Leave contact information, get theirs
Seek out contentious issue
  They will arise sooner or later
  Don’t get surprised
Use caution in defining scope, budget timing
Never promise what you cannot (personally) deliver