## Sheet1
Bar Chart Schedule | Build a swing set for Ruby
| Jan. | Feb. | Mar | Apr | May | Jun | Jul | Aug | % of Project
Activity
Order materials | [8 empty] | 10 | bar: Build a swing set for Ruby Jan. to Build a swing set for Ruby Feb.
Ship to materials to bush | [8 empty] | 5 | bar: Build a swing set for Ruby Mar
Mobilize crew | [8 empty] | 5 | bar: Build a swing set for Ruby Jun
Dig foundations | [8 empty] | 40 | bar: Build a swing set for Ruby Jun
Install swing set | [8 empty] | 30 | bar: Build a swing set for Ruby Jul
Clean up and Demob | [8 empty] | 10 | bar: Build a swing set for Ruby Aug
Planned % each month | 5 | 5 | 5 | 0 | 0 | 45 | 30 | 10 | 100
Planned Cumulative % | 5 | 10 | 15 | 15 | 15 | 60 | 90 | 100

## Sheet1 (2)
Bar Chart Schedule
| Jan. | Feb. | Mar | Apr | May | Jun | Jul | Aug | % of Project
Activity
Order materials | [8 empty] | 10 | bar: Jan. to Feb.
Ship to materials to Bush | [8 empty] | 5 | bar: Mar
Mobilize Crew | [8 empty] | 5 | bar: Jun
Dig foundatons | [8 empty] | 40 | bar: Jun
Install swing set | [8 empty] | 30 | bar: Jul
Clean up and Demob | [8 empty] | 10 | bar: Aug
Planned % each month | 5 | 5 | 5 | 0 | 0 | 45 | 30 | 10 | 100
Planned Cumulative % | 5 | 10 | 15 | 15 | 15 | 60 | 90 | 100
Actual % | 5 | 5 | 0 | 0 | 0 | 20 | 20
Actual Cumulative % | 5 | 10 | 10 | 10 | 10 | 30 | 50

## Sheet1 (3)
Bar Chart Schedule
| Jan. | Feb. | Mar | Apr | May | Jun | Jul | Aug | % of Project
Activity
Order materials | [8 empty] | 10 | bar: Jan. to Feb.
Ship to materials to Bush | [8 empty] | 5 | bar: Mar
Mobilize Crew | [8 empty] | 5 | bar: Jun
Dig foundatons | [8 empty] | 40 | bar: Jun
Install swing set | [8 empty] | 30 | bar: Jul
Clean up and Demob | [8 empty] | 10 | bar: Aug
Planned % each month | 5 | 5 | 5 | 0 | 0 | 45 | 30 | 10 | 100
Planned Cumulative % | 5 | 10 | 15 | 15 | 15 | 60 | 90 | 100
Actual % | 5 | 5 | 0 | 0 | 0 | 20 | 20
Actual Cumulative % | 5 | 10 | 10 | 10 | 10 | 30 | 50
Monthly Budget | 10000 | 10000 | 10000 | 0 | 0 | 90000 | 60000 | 20000 | 200000
Cumulative Budget | 10000 | 20000 | 30000 | 30000 | 30000 | 120000 | 180000 | 200000
Actual Monthly Cost | 5000 | 7000 | 1000 | 1000 | 0 | 50000 | 95000
Cumulative Cost | 5000 | 12000 | 13000 | 14000 | 14000 | 64000 | 159000
Cum. Cost as % of Budg. | 2.5 | 6 | 6.5 | 7 | 7 | 32 | 79.5